## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | Project Overview | MUST HAVE | No dependencies | Abhi Kavathiya | 3- Completed
Sprint 1 | Sprint 1 | US-02 | Designing the workflow and documenting project goals | MUST HAVE | Charts | Abhi Kavathiya | 3- Completed
Sprint 2 | Sprint 2 | US-03 | Exploring Documents (Agile Template,Defect Tracker,Unit Testing) | MUST HAVE | Excel Sheets | Abhi Kavathiya | 3- Completed
Sprint 2 | Sprint 2 | US-04 | Research and preparation for use case creation | MUST HAVE | W3 schools | Abhi Kavathiya | 3- Completed
Sprint 3 | Sprint 3 | US-05 | Finishing the Python Practice Set | MUST HAVE | Hackerrank | Abhi Kavathiya | 3- Completed
Sprint 4 | Sprint 4 | US-06 | Completing the Rasa Practice Set | MUST HAVE | Rasa Documentation | Abhi Kavathiya | 3- Completed
Sprint 5 | Sprint 5 | US-07 | Module 1 Discussion(Speech recognition and language processing) | MUST HAVE | Web Speech API | Abhi Kavathiya | 3- Completed
Sprint 6 | Sprint 6 | US-08 | Module 2 Discussion (Workflow Efficiency and Automation) | MUST HAVE | Pycharm | Abhi Kavathiya | 3- Completed
Sprint 7 | Sprint 7 | US-09 | Module 3 Discussion (Merging with Existing Services) | MUST HAVE | Rasa | Abhi Kavathiya | 3- Completed
Sprint 8 | Sprint 8 | US-10 | Module 4 Discussion (Verification and Deplayment) | MUST HAVE | Rasa and streamlit | Abhi Kavathiya | 3- Completed
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 57 | 31 | 21 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-01 | TID-01 | Project Overview | 2024-12-04 | 2024-12-07 | Aditya | Others | 3- Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | TID-02 | Designing the workflow and documenting project goals | 2024-12-08 | 2024-12-11 | Aditya | Design | 3- Completed | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | TID-03 | Exploring Documents (Agile Template,Defect Tracker,Unit Testing) | 2024-12-13 | 2024-12-15 | Aditya | Others | 3- Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | TID-04 | Research and preparation for use case creation | 2024-12-15 | 2024-12-17 | Aditya | Others | 3- Completed | 5 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-05 | TID-05 | Finishing the python practice set | 2024-12-18 | 2024-12-22 | Aditya | Coding | 3- Completed |  | 5 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-06 | TID-06 | Completing the rasa practice set | 2024-12-23 | 2024-12-29 | Aditya | Coding | 3- Completed | 8 | 3 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-07 | TID-07 | Module 1 Discussion(Speech recognition and language processing) | 2025-01-02 | 2025-01-07 | Aditya | Build | 3- Completed | 8 | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-08 | TID-08 | Module 2 Discussion (Workflow Efficiency and Automation) | 2025-01-09 | 2025-01-12 | Aditya | Coding | 3- Completed | 10 | 5 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-09 | TID-09 | Module 3 Discussion (Merging with Existing Services) | 2025-01-16 | 2025-01-20 | Aditya | Integration Test | 3- Completed | 11 | 4 | 3 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-10 | TID-10 | Module 4 Discussion (Verification and Deplayment) | 2025-01-23 | 2025-01-26 | Aditya | System Test | 3- Completed | 9 | 3 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 2 | Day 9 | Agile Template Discussion | Doubts cleared by mentor
Sprint 2 | Day 12 | Debugging struggle in python practice scripts | Mentor helped in finnding errors
Sprint 2 | Day 20 | confusion regarding the order of importance for use case preparation | Built a priority matrix
Sprint 3 | Day 22 | Doubts in NLP concepts | mentor took extra session
Sprint 4 | Day 24 | Longer than expected execution time for rasa queries | Took help from other members
Sprint 5 | Day 26 | Lack of access to youtube APIs | search for open source API

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | sprint 1 | Day 2 | Day 3 | Aditya | more requirements for the project | Assuming the requirements of the project are clear | Taking part in discussions and meetings | Coordinated a meeting with team and mentors to refine project goals
2 | sprint 3 | Day 12 | Day 15 | Aditya | Engaging with other memebers | Assuming the requirements of are fixed | conducting regular meetings | Improved task tracking
3 | sprint 8 | Day 20 | Day 23 | Aditya | Try more open sourse tools | Using paid api tools | Explore more api | Learned more about api integration
4
5
6
7